## 2021 Work Plan - REVISED
Tasks
2021 Middle Rio Grande Endangered Species Collaborative Program (MRGESCP) Work Plan |  | 1 | Update MRGESCP Objectives | [5 empty] | 5 | Update the Science & Adaptive Management (S&AM) Plan and Long-Term Plan
|  | 2 | Task Science & Technical (S&T) Ad Hoc Groups | [5 empty] | 6 | Implement new MRGESCP organizational structure
|  | 3 | Utilitze Conceptual Ecological Models (CEMs) | [5 empty] | 7 | Administrative tasks
|  | 4 | Improve Science Communication
TASK | SUBTASK | EC | AAH | SAMC | S&T | FPC | PST | 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01
| Executive Committee (EC) meeting | X | [7 empty] | ✓ |  |  |  | ✓ |  |  | X |  | X
| Science & Adaptive Management Committee (SAMC) meeting |  |  | X |  |  |  | ✓ | ✓ |  | ✓ |  | ✓ |  | ✓ |  |  | X
| Fiscal Planning Committee (FPC) meeting |  |  |  |  | X |  |  | ✓ |  | ✓
1a | Convene an Objectives Workshop for each species |  |  | X |  |  | X |  | ✓
1b | Report objectives and their implications for science initiatives to the EC for review and comment |  |  | X |  |  | X |  |  | ✓ | ✓
1c | Integrate objectives and strategies into the Science and Adaptive Management Information System (SAMIS) | [5 empty] | X |  |  |  |  | ✓ | ✓
2a | Form S&T Ad Hoc Groups to address specific questions |  |  | X | X |  |  | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | X | X | X | X
| Task S&T Ad Hoc Group to finalize the Rio Grande silvery minnow (RGSM) integrated population model |  |  | X | X |  |  |  |  | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | X | X
| Task S&T Ad Hoc Group to update the RGSM CEM to include genetics and augmentation components |  |  | X | X | [5 empty] | ✓ | ✓ | ✓ | ✓ | ✓ | X | X
| Task S&T Ad Hoc Group to refine the avian CEMs to include uncertainties |  |  | X | X | [5 empty] | ✓ | ✓ | ✓ | ✓ | ✓ | X | X
| Task S&T Ad Hoc Group to finalize Population Monitoring Work Group (PMWG) work in a summary report |  |  | X | X |  |  | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
| Task S&T Ad Hoc Group to develop hypotheses from the PMWG summary report |  |  | X | X | [10 empty] | X | X | X | X
| Task S&T Ad Hoc Group to develop guidance on addressing questions and challenges related to defining and documenting habitat restoration success |  |  | X | X | [10 empty] | X | X | X | X
2b | Identify critical carry-over work from past MRGESCP efforts, including panel recommendations, and begin breaking large issues into specific questions |  |  | X | X |  |  |  |  | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | X | X | X | X
2c | Develop a framework to incorporate resiliency planning into project planning design |  |  | X | [5 empty] | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | X | X | X
2d | Develop scientific activities to address questions from S&T Ad Hoc Groups and incorporate into the Project Bank |  |  | X | X | [8 empty] | ✓ | ✓ | X | X | X | X
3a | Integrate Rio Grande silvery minnow, yellow-billed cuckoo, and southwestern willow flycatcher CEMs into the SAMIS by converting schematics into graphical models and individual relationships |  |  |  | X |  | X |  | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
3b | Update RGSM CEM to include genetics and augmentation components |  |  | X | X | [5 empty] | ✓ | ✓ | ✓ | ✓ | ✓ | X | X
3c | Update avian CEMs to include levels of uncertainties |  |  |  | X | [5 empty] | ✓ | ✓ | ✓ | ✓ | ✓ | X | X
3d | Populate the Project Bank with past and current projects. Specify research hypotheses, where appropriate. |  |  | X |  |  | X |  |  | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | X | X | X | X
4a | Define the peer review process, including both internal reviews and external reviews |  |  | X |  |  | X |  |  | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | X
4b | Revise the scope of work process to incorporate the S&AM Plan elements |  |  | X |  |  | X | [5 empty] | ✓ | ✓ | ✓ | X | X | X
4c | Enhance MRGESCP science communication venues, such as seminars, workshops, and newsletters |  |  | X |  |  | X | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | X | X | X | X
| Send out regular MRGESCP newsletters | [5 empty] | X |  | ✓ |  | ✓ |  | ✓ |  | ✓ |  | ✓ |  | X
| Habitat Restoration workshop |  |  | X | [10 empty] | ✓
| Collaborative Seminar #1: 2020 RGSM Population Monitoring |  |  | X |  |  | X | [7 empty] | ✓
4d | Develop training materials and hold workshops on the SAMIS | X |  | X | X | X | X | [9 empty] | X | X | X
5a | Update the Long-Term Plan | X |  | X | [11 empty] | X | X | X | X
5b | Update the S&AM Plan |  |  |  | X | [10 empty] | X | X | X | X
6a | Update and adopt By-laws to reflect new MRGESCP structure and operations | X | X |  |  |  | X | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
6b | Draft and adopt an addendum extending the 2008 Memorandum of Agreement (MOA) | [6 empty] | ✓ | ✓ | ✓
6c | Develop processes for SAMC and FPC coordination on Collaborative Program recommendations |  |  | X |  | X | [9 empty] | X | X | X | X
6d | Draft a new MOA | X | X | [12 empty] | X | X | X | X
7a | Maintain and update documents and content on the Program Portal | [5 empty] | X | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | X | X | X | X
7b | Draft and approve the FY20 Annual Report | X |  |  |  |  | X | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7c | Update the MRGESCP contact lists to reflect changes to the new structure | X |  |  |  |  | X | ✓ | ✓ | ✓ | ✓
7d | Propose and adopt changes to cost-share | X |  |  |  |  | X |  | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7e | Develop a format for a concise Annual Report | [5 empty] | X |  |  |  | ✓ | ✓ | ✓ | ✓
7f | Develop the annual MRGESCP evaluation checklist process | X |  |  |  |  | X |  |  |  |  | ✓ | ✓ | ✓ | ✓ | X | X
7g | Begin drafting FY21 Annual Report | [5 empty] | X | [8 empty] | X | X | X | X
7h | Complete the annual MRGESCP evaluation | X |  | X |  |  | X | [9 empty] | X | X | X
7i | Develop the SAMC annual summary report |  |  | X |  |  | X | [10 empty] | X | X
7j | Develop and approve 2022 Annual Work Plan | X |  | X |  |  | X | [9 empty] | X | X | X

## 2021 Work Plan - ORIGINAL
Tasks
2021 Middle Rio Grande Endangered Species Collaborative Program (MRGESCP) Work Plan |  | 1 | Update MRGESCP Objectives | [5 empty] | 5 | Update the Science & Adaptive Management (S&AM) Plan and Long-Term Plan
|  | 2 | Task Science & Technical (S&T) Ad Hoc Groups | [5 empty] | 6 | Implement new MRGESCP organizational structure
|  | 3 | Utilitze Conceptual Ecological Models (CEMs) | [5 empty] | 7 | Administrative tasks
|  | 4 | Improve Science Communication
TASK | SUBTASK | EC | AAH | SAMC | S&T | FPC | PST | 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01
| Executive Committee (EC) meeting | X | [7 empty] | X |  |  |  | X |  |  | X |  | X
| Science & Adaptive Management Committee (SAMC) meeting |  |  | X |  |  |  | ✓ | ✓ |  | X | X |  |  |  | X | X | X
| Fiscal Planning Committee (FPC) meeting |  |  |  |  | X |  |  | ✓ |  |  | X |  |  | X |  |  | X
1a | Convene an Objectives Workshop for each species |  |  | X |  |  | X |  | ✓
1b | Report objectives and their implications for science initiatives to the EC for review and comment |  |  | X |  |  | X |  |  | ✓ | X
1c | Integrate objectives and strategies into the Adaptive Management (AM) Relational Database | [5 empty] | X |  |  |  |  | X | X
2a | Form S&T Ad Hoc Groups to address specific questions |  |  | X | X |  |  | ✓ | ✓ | ✓ | X | X | X | X | X | X | X | X | X
2b | Task S&T Ad Hoc Groups to finalize work from past scientific work groups |  |  | X | X |  |  | ✓ | ✓ | ✓
2c | Identify critical carry-over work from past MRGESCP efforts, including panel recommendations, and begin breaking large issues into specific questions |  |  | X | X |  |  |  |  | ✓ | X | X | X | X | X | X | X | X | X
2d | Consider ecosystem trends and forecasts and formulate questions to aid in future planning; develop scientific activities aimed at addressing these questions for incorporation into the Project Bank |  |  | X | [8 empty] | X | X | X | X | X | X
3a | Integrate Rio Grande silvery minnow, yellow-billed cuckoo, and southwestern willow flycatcher CEMs into the AM Relational Database by converting schematics into graphical models and individual relationships among variables |  |  |  | X |  | X |  | ✓ | ✓ | X | X | X | X
3b | Link uncertainties from CEMs to appropriate elements in the AM Relational Database |  |  | X | X |  |  |  | ✓ | ✓ | X | X | X | X | X | X | X | X | X
3c | Assess status of identified critical uncertainties from CEMs |  |  |  | X |  |  |  |  | ✓ | X | X | X | X | X | X | X | X | X
3d | Populate the Project Bank with past and current projects. Specify research hypotheses, where appropriate. |  |  | X |  |  | X |  |  | ✓ | X | X | X | X | X | X | X | X | X
3e | Develop CEMs for New Mexico meadow jumping mouse and Pecos sunflower |  |  |  | X | [11 empty] | X | X | X
4a | Define the peer review process, including both internal reviews and external reviews |  |  | X |  |  | X |  |  | ✓ | X | X | X | X | X | X
4b | Refine the writing and review processes for question-driven Summaries of Evidence |  |  | X |  |  | X | [5 empty] | X | X | X | X
4c | Revise the scope of work process to incorporate the S&AM Plan elements |  |  | X |  |  | X | [7 empty] | X | X | X | X
4d | Provide training on the AM Relational Database application | X |  | X | X | X | X | [8 empty] | X | X | X | X
5a | Update the Long-Term Plan | X |  | X | [11 empty] | X | X | X | X
5b | Update the S&AM Plan |  |  |  | X | [10 empty] | X | X | X | X
6a | Update and adopt By-laws to reflect the new MRGESCP structure and operations | X | X |  |  |  | X | ✓ | ✓ | ✓ | X | X | X | X
6b | Draft and adopt an addendum extending the 2008 Memorandum of Agreement (MOA) | [6 empty] | ✓ | ✓ | ✓
6c | Develop processes for SAMC and FPC coordination on Collaborative Program recommendations |  |  | X |  | X | [9 empty] | X | X | X | X
6d | Draft a new MOA | X | X | [13 empty] | X | X | X
7a | Maintain and update documents and content on the Program Portal | [5 empty] | X | ✓ | ✓ | ✓ | X | X | X | X | X | X | X | X | X
7b | Draft and approve the FY20 Annual Report | X |  |  |  |  | X | ✓ | ✓ | ✓ | X | X | X | X
7c | Update the MRGESCP contact lists to reflect changes to the new structure | X |  |  |  |  | X | ✓ | ✓ | ✓ | X
7d | Propose and adopt changes to cost-share | X |  |  |  |  | X |  | ✓ | ✓ | X | X | X | X
7e | Develop a format for a concise Annual Report | [5 empty] | X |  |  |  | X | X | X | X
7f | Develop the annual MRGESCP evaluation checklist process | X |  |  |  |  | X |  |  |  |  | X | X | X | X | X | X
7g | Begin drafting the FY21 Annual Report | [5 empty] | X | [8 empty] | X | X | X | X
7h | Complete the annual MRGESCP evaluation | X |  | X |  |  | X | [9 empty] | X | X | X
7i | Develop and present the SAMC's annual summary report |  |  | X |  |  | X | [10 empty] | X | X
7j | Develop and approve 2022 Annual Work Plan | X |  | X |  |  | X | [8 empty] | X | X | X | X