## Sheet1
Tasks
2022 Middle Rio Grande Endangered Species Collaborative Program (MRGESCP) Work Plan |  | 1 | Administrative tasks
|  | 2 | Task Science & Technical (S&T) Ad Hoc Groups
|  | 3 | Identify scientific uncertainties
|  | 4 | Decision tools to facilitate adaptive learning
|  | 5 | Information sharing and coordination
TASK | SUBTASK | EC | AAH | SAMC | S&T | FPC | PST | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01
| Executive Committee (EC) meeting | X | bar: 2022-03-01; 2022-06-01; 2022-09-01; 2022-12-01
| Science & Adaptive Management Committee (SAMC) meeting |  |  | X | bar: 2022-01-01; 2022-04-01; 2022-06-01; 2022-08-01; 2022-11-01
| Fiscal Planning Committee (FPC) meeting |  |  |  |  | X | bar: 2022-02-01; 2022-05-01; 2022-08-01; 2022-11-01
1a | Maintain and update documents and content on the Program Portal | [5 empty] | X | bar: 2022-01-01 to 2022-12-01
1b | Maintain and update activities in the Science and Adaptive Management Information System (SAMIS) | X |  | X |  | X | X | bar: 2022-01-01 to 2022-12-01
1c | Continue training for SAMIS | X |  | X |  |  | X | bar: 2022-01-01 to 2022-02-01
1d | Continue updating and approve the revised Science & Adaptive Management Plan | X |  | X |  |  | X | bar: 2022-01-01 to 2022-03-01
1e | Complete and present results from the annual MRGESCP evaluation | X |  | X |  |  | X | bar: 2022-01-01 to 2022-03-01
1f | New SAMC member search and approval of new members | X |  |  |  |  | X | bar: 2022-01-01 to 2022-03-01
1g | Finalize and adopt a new Memorandum of Agreement (MOA) | X | X | bar: 2022-01-01 to 2022-03-01
1h | Continue drafting and approve the 2021 Annual Report | X |  |  |  |  | X | bar: 2022-01-01 to 2022-03-01
1i | Implement agreed upon changes from the annual evaluation | X |  | X |  |  | X | bar: 2022-04-01 to 2022-05-01
1j | Begin drafting 2022 Annual Report | [5 empty] | X | bar: 2022-09-01 to 2022-12-01
1k | Finalize 2022 signatory contributions reports | [5 empty] | X | bar: 2022-11-01 to 2022-12-01
1l | Develop the SAMC annual summary report |  |  | X |  |  | X | bar: 2022-11-01 to 2022-12-01
1m | Develop and approve 2023 Annual Work Plan | X |  | X |  |  | X | bar: 2022-10-01 to 2022-12-01
2a | Initiate an Internal Science Review of the draft revised Rio Grande Silvery Minnow (RGSM) Conceptual Ecological Model (CEM) |  |  | X | X |  | X | bar: 2022-02-01 to 2022-03-01
2b | Continue the Rio Grande Silvery Minnow Hypothesis Development S&T Ad Hoc Group |  |  |  | X | bar: 2022-01-01 to 2022-05-01
2c | Convene Habitat Restoration (HR) Guidance S&T Ad Hoc Groups to develop species-specific restoration goals, monitoring considerations, and metrics to document success |  |  |  | X | bar: 2022-01-01 to 2022-07-01
2d | Organize and convene a Scenario Planning S&T Ad Hoc Group to identify ways to incorporate resiliency into the MRGESCP long-term planning and decision support |  |  |  | X | bar: 2022-01-01 to 2022-07-01
2e | Organize and convene a New Mexico Meadow Jumping Mouse CEM Development S&T Ad Hoc Group |  |  |  | X | bar: 2022-07-01 to 2022-12-01
2f | Organize and convene a Pecos Sunflower CEM Development S&T Ad Hoc Group |  |  |  | X | bar: 2022-07-01 to 2022-12-01
3a | Strategically identify uncertainties in the CEMs and link them to the appropriate elements in SAMIS |  |  |  | X |  | X | bar: 2022-01-01 to 2022-07-01
3b | Assess status of identified critical uncertainties |  |  | X | X | bar: 2022-04-01 to 2022-09-01
3c | Populate the Project Bank with past and current projects. Specify research hypotheses, where appropriate. |  |  | X |  |  | X | bar: 2022-01-01 to 2022-12-01
4a | Conduct a survey of management needs regarding Rio Grande silvery minnow population monitoring |  |  | X |  |  | X | bar: 2022-03-01 to 2022-06-01
4b | Evaluate and refine Project Bank scoring rubric to align with management needs |  |  | X |  |  | X | bar: 2022-04-01 to 2022-10-01
4c | Plan for and host the Collaboratory | X |  | X |  |  | X | bar: 2022-09-01 to 2022-12-01
5a | Send out regular MRGESCP newsletters | [5 empty] | X | bar: 2022-02-01; 2022-04-01; 2022-06-01; 2022-08-01; 2022-10-01; 2022-12-01
5b | Host quarterly HR coordination meetings |  |  |  |  | X | X | bar: 2022-02-01; 2022-05-01; 2022-08-01; 2022-11-01
5c | Coordinate on fulfilling project needs that were identified at the HR coordination meetings |  |  |  |  | X | bar: 2022-02-01; 2022-05-01; 2022-08-01; 2022-11-01
5d | Host seminars to present on specific topics or projects | [5 empty] | X