## 2023 Work Plan_Prop Revs
Middle Rio Grande Endangered Species Collaborative Program 2023 Work Plan - Revision proposed 09/28/2023
| TASK | SUBTASK | EC | AAH | SAMC | S&T | FPC | Sigs | PST | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01
|  | Executive Committee (EC) meeting | X | bar: 2023-01-01 to 2023-12-01
|  | Science and Adaptive Management Committee (SAMC) meeting |  |  | X | bar: 2023-01-01 to 2023-12-01
|  | Fiscal Planning Committee (FPC) meeting |  |  |  |  | X | bar: 2023-01-01 to 2023-12-01
General Collaborative Program Administration | 1.1 | Program Portal Administration
| 1.1a | Maintain and update documents and content on the Program Portal | [6 empty] | X | bar: 2023-01-01 to 2023-12-01
| 1.1b | Update the existing datasets on the Program Portal | [5 empty] | X | X | bar: 2023-01-01 to 2023-11-01
| 1.1c | Develop a plan for continued Program Portal funding | X |  |  |  | X | bar: 2023-01-01 to 2023-12-01
| 1.2 | Science and Adaptive Management Information System (SAMIS)
| 1.2a | Maintain and update activities in SAMIS | [5 empty] | X | X | bar: 2023-01-01 to 2023-12-01
| 1.2b | Finish module one of signatory SAMIS trainings | X |  | X |  |  | X | X | bar: 2023-01-01 to 2023-03-01
| 1.3 | SAMC Membership
| 1.3a | Collect applications for new SAMC members | [6 empty] | X | bar: 2023-01-01 to 2023-03-01
| 1.3b | Appoint new SAMC members | X | X | bar: 2023-03-01
| 1.4 | Science Evaluation
| 1.4a | Carry out the Science Evaluation based on the outcomes of the 2022 Collaboratory |  |  | X |  |  |  | X | bar: 2023-01-01 to 2023-03-01; 2023-06-01 to 2023-11-01
| 1.4b | Complete and present results from the Science Evaluation | X |  | X |  |  |  | X | bar: 2023-03-01; 2023-11-01
| 1.5 | Annual Program Evaluation
| 1.5a | Carry out the Annual Program Evaluation | X |  | X |  | X |  | X | bar: 2023-01-01 to 2023-03-01
| 1.5b | Complete and present results from the Annual Program Evaluation | X | [5 empty] | X | bar: 2023-03-01
| 1.5c | If needed, draft and adopt updates to the Long-Term Plan for Science & Adaptive Management to reflect recommendations from the Science Evaluation and Program Evaluation |  | X |  |  |  |  | X | bar: 2023-01-01 to 2023-03-01
| 1.5d | If needed, draft and adopt updates to committee charters and the By-Laws to reflect recommendations from the Program Evaluation | X | X |  |  |  |  | X | bar: 2023-04-01 to 2023-06-01
| 1.6 | Work Plan
| 1.6a | Check in and revise the 2023 Work Plan if needed | X | [5 empty] | X | bar: 2023-03-01; 2023-06-01; 2023-09-01
| 1.6b | Develop and approve the 2024 Work Plan | X | [5 empty] | X | bar: 2023-10-01 to 2023-12-01
| 1.7 | Reporting
| 1.7a | Continue drafting and approve the 2022 Annual Report | X | [5 empty] | X | bar: 2023-01-01 to 2023-03-01
| 1.7b | Collect and finalize 2022 signatory contributions reports | [5 empty] | X | X | bar: 2023-01-01 to 2023-09-01
| 1.7c | Develop and finalize the 2022 cost share report | [5 empty] | X | X | bar: 2023-01-01 to 2023-09-01
| 1.7d | Begin drafting the 2023 Annual Report | [5 empty] | X | X | bar: 2023-10-01 to 2023-12-01
| 1.7e | Develop the SAMC annual summary presentation to the EC |  |  | X |  |  |  | X | bar: 2023-11-01 to 2023-12-01
Communication and Information Sharing | 2.1 | Send out regular MRGESCP newsletters | [6 empty] | X | bar: 2023-02-01; 2023-04-01; 2023-06-01; 2023-08-01; 2023-10-01; 2023-12-01
| 2.2 | Host regular collaborative seminars |  |  | X |  |  |  | X | bar: 2023-02-01; 2023-05-01 to 2023-06-01; 2023-08-01 to 2023-09-01
| 2.3 | 2023 Science Symposium
| 2.3a | Approve the proposal for the 2023 Science Symposium | X | bar: 2023-06-01
| 2.3b | Collect abstracts for the 2023 Science Symposium | [6 empty] | X | bar: 2023-07-01 to 2023-10-01
| 2.3c | Finalize the agenda for the 2023 Science Symposium |  |  | X |  |  |  | X | bar: 2023-11-01
| 2.3d | Host the 2023 Science Symposium | X |  | X |  |  |  | X | bar: 2023-12-01
Science Decision Support Planning and Tools Development | 3.1 | Information and Data Quality Standards
| 3.1a | Convene the hybrid ad hoc group to discuss data and information quality standards | X | X | X | X | bar: 2023-02-01 to 2023-12-01
| 3.1b | Develop a project template to document data and information quality standards for signatory projects | X |  | X | bar: 2023-10-01 to 2023-12-01
| 3.2 | Survey of Manager Confidence in MRGESCP Science Support | X | [5 empty] | X | bar: 2023-11-01 to 2023-12-01
| 3.2a | Present results of the 2022 survey | X | [5 empty] | X | bar: 2023-03-01
| 3.2b | Incorporate the objective of the survey of manager confidence into the Annual Program Evaluation for 2023 | [6 empty] | X | bar: 2023-11-01 to 2023-12-01
| 3.3 | Evaluate and refine project evaluation criteria to align with management needs |  |  | X | bar: 2023-01-01 to 2023-12-01
| 3.4 | Conceptual Ecological Models
| 3.4a | Complete the revisions to the Rio Grande Silvery Minnow (RGSM) Conceptual Ecological Model to incorporate genetics considerations and the augmentation program |  |  | X | X | bar: 2023-01-01 to 2023-10-01
| 3.4b | Initiate an Internal Science Review of the draft revised Rio Grande Silvery Minnow (RGSM) Conceptual Ecological Model |  |  | X | X |  |  | X | bar: 2023-11-01 to 2023-12-01
| 3.4c | Draft a conceptual ecological model for the New Mexico meadow jumping mouse |  |  | X | X |  |  | X | bar: 2023-01-01 to 2023-09-01
| 3.4d | Draft a conceptual ecological model for the Pecos sunflower |  |  | X | X |  |  | X | bar: 2023-04-01 to 2023-09-01
| 3.5 | Climate Scenario Futures Planning Workshop
| 3.5a | Plan Climate Scenario Futures Planning Workshop for the Middle Rio Grande to develop strategies for managing listed species in the future |  |  | X |  |  |  | X | bar: 2023-02-01 to 2023-09-01
| 3.5b | Link climate forecast models with projected on-the-ground impacts to species and habitat |  |  | X |  |  |  | X | bar: 2023-04-01 to 2023-06-01
Host a field trip to the Whitfield Wildlife Conservation Area | bar: 2023-09-01
| 3.5c | Host a Climate Scenario Futures Planning Workshop | X |  | X |  |  |  | X | bar: 2023-10-01
| 3.5d | Compile and present results from Climate Scenario Futures Planning Workshop |  |  | X |  |  |  | X | bar: 2023-11-01 to 2023-12-01
Implementing Adaptive Management Activities | 4.1 | Continue RGSM Hypothesis Development S&T Ad Hoc Group |  |  |  | X | bar: 2023-03-01 to 2023-05-01; 2023-10-01 to 2023-12-01
| 4.1a | Explore research hypotheses regarding the influence of mesohabitat on fish distribution (Rec #4) |  |  |  | X | bar: 2023-01-01 to 2023-05-01; 2023-10-01 to 2023-12-01
| 4.1b | Compare and contrast various RGSM population models, and determine most appropriate uses for each (Rec #7) |  |  |  | X | bar: 2023-01-01 to 2023-05-01; 2023-10-01 to 2023-12-01
| 4.2 | Provide Recommendations for Drying in the Angostura Reach
| 4.2a | Survey of water managers regarding roles and flexibility in planning for and controlling drying |  |  |  | X |  |  | X | bar: 2023-01-01 to 2023-03-01
| 4.2b | Provide recommendations for management actions and data collection in response to potential drying in the Angostura reach in 2023 | X |  | X | X |  |  | X | bar: 2023-04-01 to 2023-05-01
| 4.2c | Develop public messaging strategies in concert with recommendations for drying in 2023 | X | X |  |  |  |  | X
| 4.2e | Evaluate effectiveness of the drying response plan, and refine recommendations for 2024 (contingent on drying in Angostura Reach) | X |  | X | X |  |  | X
| 4.3 | Convene Restoration Guidance S&T Ad Hoc Groups to define restoration goals, monitoring/maintenance considerations, and metrics to document success
| 4.3a | Research Society of Ecological Resotration (SER) Recovery Wheel and prepare ad hoc group charge |  |  | X |  |  |  | X | bar: 2023-05-01 to 2023-08-01
| 4.3b | Evaluate use of the Society of Ecological Restoration (SER) Recovery Wheel's applicability and usefulness to plan and evaluate ecosystem restoration in the MRG |  |  | X | X | bar: 2023-09-01 to 2023-12-01
| 4.3c | Compile a compendium of restoration resources for the MRG |  |  | X |  |  |  | X | bar: 2023-05-01 to 2023-08-01
| 4.3c | Review the draft compendium of restoration resources for the MRG and provide additional resources for inclusion |  |  | X | X |  |  | X | bar: 2023-09-01 to 2023-12-01
| 4.4 | Vegetated Islands and Bank-Attached Bars in the MRG
| 4.4a | Develop a glossary of technical terms related to management of vegetated islands/bars |  |  | X |  |  |  | X | bar: 2023-05-01 to 2023-12-01
| 4.4b | Develop conceptual model representing the vegetated islands/bars phenomenon |  |  | X |  |  |  | X | bar: 2023-09-01 to 2023-12-01
Coordination of Signatory Activities | 5.1 | Host quarterly HR coordination meetings |  |  |  |  | X |  | X | bar: 2023-02-01; 2023-05-01; 2023-08-01; 2023-11-01
| 5.2 | Identify coordination opportunities related to the spring/summer hydrology | X |  |  |  |  | X | bar: 2023-03-01
| 5.3 | Provide updates on coordination activities related to the spring/summer hydrology, and lessons learned | X |  |  |  |  | X | bar: 2023-12-01
| 5.4 | Provide updates on the implementation of signatory activities from the Long-Term Plan |  |  |  |  | X | X | bar: 2023-01-01; 2023-04-01; 2023-07-01; 2023-10-01

## 2023 Work Plan_June 2023
Middle Rio Grande Endangered Species Collaborative Program 2023 Work Plan
| TASK | SUBTASK | EC | AAH | SAMC | S&T | FPC | Sigs | PST | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01
|  | Executive Committee (EC) meeting | X | bar: 2023-01-01 to 2023-12-01
|  | Science and Adaptive Management Committee (SAMC) meeting |  |  | X | bar: 2023-01-01 to 2023-12-01
|  | Fiscal Planning Committee (FPC) meeting |  |  |  |  | X | bar: 2023-01-01 to 2023-12-01
General Collaborative Program Administration | 1.1 | Program Portal Administration
| 1.1a | Maintain and update documents and content on the Program Portal | [6 empty] | X | bar: 2023-01-01 to 2023-12-01
| 1.1b | Update the existing datasets on the Program Portal | [5 empty] | X | X | bar: 2023-01-01 to 2023-07-01
| 1.1c | Upload new datasets on the Program Portal identified at the 2022 Portal Stakeholder Meetings | [5 empty] | X | X | bar: 2023-01-01 to 2023-07-01
| 1.1d | Develop a plan for continued Program Portal funding | X |  |  |  | X | bar: 2023-01-01 to 2023-07-01
| 1.2 | Science and Adaptive Management Information System (SAMIS)
| 1.2a | Maintain and update activities in SAMIS | [5 empty] | X | X | bar: 2023-01-01 to 2023-12-01
| 1.2b | Finish module one of signatory SAMIS trainings | X |  | X |  |  | X | X | bar: 2023-01-01 to 2023-03-01
| 1.3 | SAMC Membership
| 1.3a | Collect applications for new SAMC members | [6 empty] | X | bar: 2023-01-01 to 2023-03-01
| 1.3b | Appoint new SAMC members | X | X | bar: 2023-03-01
| 1.4 | Science Evaluation
| 1.4a | Carry out the Science Evaluation based on the outcomes of the 2022 Collaboratory |  |  | X |  |  |  | X | bar: 2023-01-01 to 2023-03-01
| 1.4b | Complete and present results from the Science Evaluation | X |  | X |  |  |  | X | bar: 2023-03-01
| 1.5 | Annual Program Evaluation
| 1.5a | Carry out the Annual Program Evaluation | X |  | X |  | X |  | X | bar: 2023-01-01 to 2023-03-01
| 1.5b | Complete and present results from the Annual Program Evaluation | X | [5 empty] | X | bar: 2023-03-01
| 1.5c | If needed, draft and adopt updates to the Long-Term Plan for Science & Adaptive Management to reflect recommendations from the Science Evaluation and Program Evaluation |  | X |  |  |  |  | X | bar: 2023-01-01 to 2023-03-01
| 1.5d | If needed, draft and adopt updates to committee charters and the By-Laws to reflect recommendations from the Program Evaluation | X | X |  |  |  |  | X | bar: 2023-04-01 to 2023-06-01
| 1.6 | Work Plan
| 1.6a | Check in and revise the 2023 Work Plan if needed | X | [5 empty] | X | bar: 2023-03-01; 2023-06-01; 2023-09-01
| 1.6b | Develop and approve the 2024 Work Plan | X | [5 empty] | X | bar: 2023-10-01 to 2023-12-01
| 1.7 | Reporting
| 1.7a | Continue drafting and approve the 2022 Annual Report | X | [5 empty] | X | bar: 2023-01-01 to 2023-03-01
| 1.7b | Collect and finalize 2022 signatory contributions reports | [5 empty] | X | X | bar: 2023-01-01 to 2023-09-01
| 1.7c | Develop and finalize the 2022 cost share report | [5 empty] | X | X | bar: 2023-01-01 to 2023-09-01
| 1.7d | Begin drafting the 2023 Annual Report | [5 empty] | X | X | bar: 2023-10-01 to 2023-12-01
| 1.7e | Develop the SAMC annual summary presentation to the EC |  |  | X |  |  |  | X | bar: 2023-11-01 to 2023-12-01
Communication and Information Sharing | 2.1 | Send out regular MRGESCP newsletters | [6 empty] | X | bar: 2023-02-01; 2023-04-01; 2023-06-01; 2023-08-01; 2023-10-01; 2023-12-01
| 2.2 | Host regular collaborative seminars |  |  | X |  |  |  | X | bar: 2023-03-01; 2023-06-01; 2023-09-01; 2023-12-01
| 2.3 | 2023 Science Symposium
| 2.3a | Approve the proposal for the 2023 Science Symposium | X | bar: 2023-06-01
| 2.3b | Collect abstracts for the 2023 Science Symposium | [6 empty] | X | bar: 2023-07-01 to 2023-10-01
| 2.3c | Finalize the agenda for the 2023 Science Symposium |  |  | X |  |  |  | X | bar: 2023-11-01
| 2.3d | Host the 2023 Science Symposium | X |  | X |  |  |  | X | bar: 2023-12-01
Science Decision Support Planning and Tools Development | 3.1 | Information and Data Quality Standard
| 3.1a | Convene the hybrid ad hoc group to discuss data and information quality standards | X | X | X | X | bar: 2023-02-01 to 2023-12-01
| 3.1b | Develop a project template to document data and information quality standards for signatory projects | X |  | X
| 3.2 | Survey of Manager Confidence in MRGESCP Science Support | X | [5 empty] | X | bar: 2023-11-01 to 2023-12-01
| 3.2a | Present results of the 2022 survey | X | [5 empty] | X | bar: 2023-03-01
| 3.2b | Incorporate the objective of the survey of manager confidence into the Annual Program Evaluation for 2023 | [6 empty] | X | bar: 2023-11-01 to 2023-12-01
| 3.3 | Evaluate and refine project evaluation criteria to align with management needs |  |  | X | bar: 2023-01-01 to 2023-08-01
| 3.4 | Conceptual Ecological Models
| 3.4a | Complete the revisions to the Rio Grande Silvery Minnow (RGSM) Conceptual Ecological Model to incorporate genetics considerations and the augmentation program |  |  | X | X | bar: 2023-01-01 to 2023-05-01
| 3.4b | Initiate an Internal Science Review of the draft revised Rio Grande Silvery Minnow (RGSM) Conceptual Ecological Model |  |  | X | X |  |  | X | bar: 2023-06-01 to 2023-08-01
| 3.4c | Draft a conceptual ecological model for the New Mexico meadow jumping mouse |  |  | X | X |  |  | X | bar: 2023-01-01 to 2023-07-01
| 3.4d | Draft a conceptual ecological model for the Pecos sunflower |  |  | X | X |  |  | X | bar: 2023-04-01 to 2023-07-01
| 3.5 | Climate Scenario Planning Workshop
| 3.5a | Plan Climate Scenario Planning Workshop for the Middle Rio Grande to develop strategies for managing listed species in the future |  |  | X |  |  |  | X | bar: 2023-02-01 to 2023-09-01
| 3.5b | Link climate forecast models with projected on-the-ground impacts to species and habitat |  |  | X |  |  |  | X | bar: 2023-04-01 to 2023-06-01
Host a field trip to the Whitfield Wildlife Conservation Area | bar: 2023-09-01
| 3.5c | Host a Climate Scenario Planning Workshop | X |  | X |  |  |  | X | bar: 2023-10-01
| 3.5d | Compile and present results from Climate Scenario Planning Workshop |  |  | X |  |  |  | X | bar: 2023-11-01 to 2023-12-01
| 3.6 | Send a survey to solicit input and feedback on data relationship visualization options for the Program Portal | [5 empty] | X | X | bar: 2023-06-01 to 2023-08-01
Implementing Adaptive Management Activities | 4.1 | Continue RGSM Hypothesis Development S&T Ad Hoc Group |  |  |  | X | bar: 2023-03-01 to 2023-05-01
| 4.1a | Explore research hypotheses regarding the influence of mesohabitat on fish distribution (Rec #4) |  |  |  | X | bar: 2023-01-01 to 2023-05-01
| 4.1b | Compare and contrast various RGSM population models, and determine most appropriate uses for each (Rec #7) |  |  |  | X | bar: 2023-01-01 to 2023-05-01
| 4.2 | Provide Recommendations for Drying in the Angostura Reach
| 4.2a | Survey of water managers regarding roles and flexibility in planning for and controlling drying |  |  |  | X |  |  | X | bar: 2023-01-01 to 2023-03-01
| 4.2b | Provide recommendations for management actions and data collection in response to potential drying in the Angostura reach in 2023 | X |  | X | X |  |  | X | bar: 2023-04-01 to 2023-05-01
| 4.2c | Develop public messaging strategies in concert with recommendations for drying in 2023 | X | X |  |  |  |  | X | bar: 2023-05-01 to 2023-06-01
| 4.2e | Evaluate effectiveness of the drying response plan, and refine recommendations for 2024 (contingent on drying in Angostura Reach) | X |  | X | X |  |  | X | bar: 2023-09-01 to 2023-12-01
| 4.3 | Convene Restoration Guidance S&T Ad Hoc Groups to define restoration goals, monitoring/maintenance considerations, and metrics to document success
| 4.3a | Evaluate use of the Society of Ecological Restoration (SER) Recovery Wheel's applicability and usefulness to plan and evaluate ecosystem restoration in the MRG |  |  | X | X | bar: 2023-04-01 to 2023-11-01
| 4.3b | Compile and review a compendium of restoration resources for the MRG |  |  | X | X | bar: 2023-03-01 to 2023-11-01
| 4.4 | Vegetated Islands and Bank-Attached Bars in the MRG
| 4.4a | Develop a glossary of technical terms related to management of vegetated islands/bars |  |  | X | X | bar: 2023-05-01 to 2023-07-01
| 4.4b | Develop conceptual model representing the vegetated islands/bars phenomenon |  |  | X | X | bar: 2023-05-01 to 2023-07-01
Coordination of Signatory Activities | 5.1 | Host quarterly HR coordination meetings |  |  |  |  | X |  | X | bar: 2023-02-01; 2023-05-01; 2023-08-01; 2023-11-01
| 5.2 | Identify coordination opportunities related to the spring/summer hydrology | X |  |  |  |  | X | bar: 2023-03-01
| 5.3 | Provide updates on coordination activities related to the spring/summer hydrology, and lessons learned | X |  |  |  |  | X | bar: 2023-12-01
| 5.4 | Provide updates on the implementation of signatory activities from the Long-Term Plan |  |  |  |  | X | X | bar: 2023-01-01; 2023-04-01; 2023-07-01; 2023-10-01